Digital marketing plan

[Business name]  ·  [Period]  ·  Owner: [Name]

Guidance: Fill the one-page plan first. Everything after it is the schedule that makes the plan happen — if the one page is vague, the schedule will be busywork.

The one-page plan

Objective

Guidance: The commercial result, with a number and a date.

[ ................................................................................ ]

Audience

Guidance: Who, and the trigger that starts them looking.

[ ................................................................................ ]

Offer

Guidance: What you are selling and the reason to choose it.

[ ................................................................................ ]

Channels

Guidance: Maximum three, each with the job it does.

[ ................................................................................ ]

Not doing

Guidance: What you are deliberately leaving out this period.

[ ................................................................................ ]

Key activities

Guidance: The five things that must actually happen.

[ ................................................................................ ]

Owner per activity

Guidance: A name against each. Not a team.

[ ................................................................................ ]

Budget split

Guidance: Media / production / tools.

[ ................................................................................ ]

Primary metric

Guidance: The single number that decides whether this worked.

[ ................................................................................ ]

Review date

Guidance: When you will judge it, booked in a calendar now.

[ ................................................................................ ]

Worked example

Illustrative. Not a real business and not a benchmark.

| Field | Example |
| --- | --- |
| Business | Example Co, a 12-person B2B services firm (illustrative) |
| Objective | Increase qualified enquiries from 8 to 20 a month by the end of Q3. |
| Audience | Operations managers at 50–250 person companies, triggered by a failed audit or a new regulation. |
| Offer | A fixed-price compliance review, positioned as the cheapest way to find out where you stand. |
| Channels | Depth content on the trigger events; paid search on problem-aware terms; a partner referral programme. |
| Not doing | Paid social, general brand content, conference sponsorship. |
| Primary metric | Enquiries meeting the qualification criteria. |
| Budget split | 60% media, 30% production, 10% tools |
| Biggest risk | The subject-matter expert has four hours a month. If content depends on more, the plan fails in month two. |

Quarterly shape

Guidance: A starting sequence. Adjust the themes; keep the principle that measurement precedes spending.

| Quarter | Focus | Why |
| --- | --- | --- |
| Q1 | Fix measurement, then publish | Nothing else is worth doing until the numbers are trustworthy. |
| Q2 | Scale what worked in Q1 | Double down before adding anything new. |
| Q3 | Add one channel, carefully | One, with a stated hypothesis and a kill date. |
| Q4 | Convert and consolidate | Retention and repeat purchase are cheaper than acquisition. |

Plan or strategy?

Guidance: If you are unsure which document you are writing, this table settles it.

| Question | Strategy | Plan |
| --- | --- | --- |
| What it answers | Where are we going, and what are we not doing? | What happens, when, who does it, what it costs. |
| Time horizon | A year or more | A quarter to a year, in months |
| Changes when | The market or the business model changes | Monthly, as work completes or slips |
| Length | One page | One page plus a schedule |
| Fails by | Listing everything instead of choosing | Having no owner or date against anything |

Common mistakes

- Writing a plan with no owner against any line, so nothing is anybody’s job.

- Planning twelve months of activity in month one, then abandoning it in month three when reality intervenes.

- Listing channels without saying what each is for, which makes it impossible to judge whether one is working.

- No stated budget split, so media quietly consumes the production budget.

- No review date, which means the plan is never formally wrong and never formally updated.

- Confusing the plan with the strategy: a plan that has to answer "where are we going" will be out of date immediately.

Template from digitalmarketingmind.com/templates/digital-marketing-plan/  ·  Created by Alston Antony  ·  Free to use in your own client work.